## Sheet1
Concern/bugs | App/System | Dev comment
mag add ko picture sng resident wla ga save ang new record | App or System? | Working on System
ang apk version gale dayun |  | To be followed
paano makamsg si security sa resident, wala sms sa security app |  | Automatic ang system ma send sms sa contact persons ka household if may visitor. No need for human intervention
pano ea ang push notif? |  | For option ni siya. To be replaced with sms notif. Budlay ni siya sa type sang environment ka app ta. Please identify kung sa diin pa gd ang need sms notif
if possible, pwede tani butangan back button
wala pain nga qr code for vehicle para e print tani for sticker |  | For Development on App and new Dashboard or include in household in System
sa resident side, ang report if acknowledge na, ma appear nlng tani automatic |  | to notify user through sms. Para ma check and reload niya sa app
API |  | ?
mag refresh, ga log out |  | no need for concern since apk ang gamiton. Nd ni siya ma refresh
ang sa maintenance, kung mag create, ang created by ga null - null ang updated by |  | Working on System. Please send screenshot and copy of database
mag add ang resident sang family member, pano bi kung naka register na nga resident ang inog add ea |  | For development - add search function for adding new household member in app
list of all resident ang visitor logs, pwede tani ma filte | App or system? | System - Resident Logs can be found on residents Dashboard (View Gate Logs), HouseHold Visitor logs can be found on Household Dashboard -> Visitor Logs, Household member gate logs can be found on HouseHold dashboard -> Member logs
vehicle logs |  | Ok for Development, Resident app -> to add on Vehicles section, on system to add on Household Dashboard
added new vehicle but not showing | Confirmed bug | To be rechecked on next release
purpose of generate report |  | For update of Graph data based on date range - Graph on dashboard displays the frequency of resident reports within given date range